# Initial Project Planning Template

| Date | 02 October 2026 |
| --- | --- |
| Team ID | SWTID-2026-6594 |
| Project Name | PocketSmart AI |
| Maximum Marks | 5 Marks |

## Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create a product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members | Sprint Start Date | Sprint End Date (Planned) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Data Generation | USN-1 | As a developer, I can generate 30 months of seeded synthetic transactions with 10 categories and injected anomalies. | 3 | High | Mukilkani R P | 28 Sep 2026 | 30 Sep 2026 |
| Sprint-1 |  | USN-2 | As a tester, I have 300 hand-labelled merchant strings to validate the classifier. | 2 | High | Chandru S | 28 Sep 2026 | 30 Sep 2026 |
| Sprint-1 | Merchant Classification | USN-3 | As a user, I can get a spending category for any merchant string so my spending is organized. | 5 | High | Mukilkani R P | 28 Sep 2026 | 30 Sep 2026 |
| Sprint-1 |  | USN-4 | As a user, I can see the confidence of each category prediction. | 2 | Medium | Mukilkani R P | 28 Sep 2026 | 30 Sep 2026 |
| Sprint-2 | Anomaly Detection | USN-5 | As a user, I can see unusual transactions flagged against my normal per-category spending. | 3 | Medium | Mukilkani R P | 30 Sep 2026 | 02 Oct 2026 |
| Sprint-2 | Forecasting | USN-6 | As a user, I can see next-week spend forecast per category, compared against baselines. | 5 | High | Mukilkani R P | 30 Sep 2026 | 02 Oct 2026 |
| Sprint-2 |  | USN-7 | As a developer, I can regenerate all evaluation metrics and plots with one command. | 3 | High | Mukilkani R P | 30 Sep 2026 | 02 Oct 2026 |
| Sprint-2 | REST API | USN-8 | As a user, I can call /categorize, /summary, /forecast, /anomalies and /advice with validated inputs. | 5 | High | Mukilkani R P | 30 Sep 2026 | 02 Oct 2026 |
| Sprint-3 | AI Advice | USN-9 | As a user, I receive plain-English advice that still works when the Gemini API is unreachable. | 5 | High | Mukilkani R P | 02 Oct 2026 | 03 Oct 2026 |
| Sprint-3 | Frontend | USN-10 | As a user, I can use a simple web interface instead of calling the API by hand. | 5 | Medium | Prabhagaran E | 02 Oct 2026 | 03 Oct 2026 |
| Sprint-3 | Deployment | USN-11 | As a user, I can open the app through a public Cloud Run URL on my phone. | 3 | High | Mukilkani R P | 02 Oct 2026 | 03 Oct 2026 |
| Sprint-3 | Documentation | USN-12 | As a team, we have the lab report, PPT and demo script ready for submission. | 3 | Medium | Naveen K, Chandru S | 02 Oct 2026 | 03 Oct 2026 |